**MomsPRN MILESTONE SUMMARY DOCUMENT**

|  |  |  |
| --- | --- | --- |
| Rhode Island Moms PRN Milestone Summary | | |
| Deliverable | **Timeframe Due Dates** | **Notes** |
| Utilize the RI Moms PRN provider teleconsultation line as needed | Starting February 2021 | [RI MomsPRN WIH Website](https://www.womenandinfants.org/ri-momsprn) |
| QI team participation in monthly meetings with the practice QI facilitator | March 2021 - April 2022 | N/A |
| Identify members of the practice quality improvement (QI) team. The team should consist of 3 to 4 staff in different roles and include a practice clinical champion and an IT/EHR staff member. Complete [Provider Email List](https://www.ctc-ri.org/sites/default/files/uploads/Provider%20Email%20List%20-%20Cohort%202.xlsx). | March 9, 2021 | Completed with the Practice Facilitator – details to be submitted to [RIDOH@ctc-ri.org](mailto:RIDOH@ctc-ri.org).  [Provider Email List Template](https://www.ctc-ri.org/sites/default/files/uploads/7.%20Provider%20Email%20List%20Template%20-%20Cohort%202.xlsx) to be submitted to RIDOH@ctc-ri.org. |
| * Identify IT team * IT team to meet with RIDOH/CTC within first three months. May take place at scheduled facilitation meeting. * Test IT plan for documentation of screening results and submission data | RIDOH/CTC IT Team Meeting: March 2021, date TBD  Test IT Plan : April 2021 | [Screening Tool Resource – Measurement Information](https://www.ctc-ri.org/sites/default/files/uploads/RI%20MomsPRN%20Screening%20Tool%20Resource%2012.23.2020.docx)  [Work Flow Tool](https://www.ctc-ri.org/sites/default/files/uploads/12.%20MomsPRN%20Workflow%20Checklist.doc)  [Work Flow Example](https://www.ctc-ri.org/sites/default/files/uploads/11.%20MomsPRN%20Example%20workflow.pdf)  [Measurement Specification Guide](https://www.ctc-ri.org/sites/default/files/uploads/RI%20MomsPRN%20Cohort%202%20Measure%20Specification%20Guide%2003.15.21%20Version.pdf) |
| 1. Each provider must complete survey within 45 days of award notification: [Survey Monkey](https://www.surveymonkey.com/r/MC6RPX3)   Complete the practice self-efficacy survey with practice facilitator | Due by: April 9, 2021  To be completed at first practice facilitation meeting | Provider Survey:  <https://www.surveymonkey.com/r/MC6RPX3>  Practice Survey:  <https://www.surveymonkey.com/r/GHJ3Z89>  Practice survey details to be submitted to [RIDOH@ctc-ri.org](mailto:RIDOH@ctc-ri.org) by Practice Facilitator |
| Clinical team to meet with Eva Ray during first three months.   1. Select evidence-based tools | February - April 2021 | Evidence based tools needs to be incorporated in EHR. |
| Screen for perinatal depression, anxiety and substance use with validated screening tool(s) | April 2021 - March 2022 | N/A |
| Submit a baseline report of screening rates for perinatal depression, anxiety, and substance use | April 9, 2021 | Submit via link at: [MomsPRN Data Reporting](https://www.tfaforms.com/4772053)  Alternative: Submit using [Excel Spreadsheet](https://www.ctc-ri.org/sites/default/files/uploads/12.%20RI%20MomsPRN%20Measure%20Reporting%20Template%2003.15.21%20Version.xlsx) and email to: jarruda@ctc-ri.org |
| Develop draft workflows to implement screening for perinatal depression, anxiety and substance use with validated screening tool(s) | April 30, 2021 | [Work Flow Tool](https://www.ctc-ri.org/sites/default/files/uploads/12.%20MomsPRN%20Workflow%20Checklist.doc)  [Work Flow Example](https://www.ctc-ri.org/sites/default/files/uploads/11.%20MomsPRN%20Example%20workflow.pdf) |
| Deliverable | **Timeframe Due Dates** | **Notes** |
| In conjunction with the QI practice facilitator, identify quality improvement activities to optimize perinatal behavioral health screening, treatment and referral | Due by: May 7, 2021 *Due Month after baseline data submissions* | [Plan-Do-Study-Act (PDSA)](https://www.ctc-ri.org/sites/default/files/uploads/4.%20PDSAWorksheetforTestingChanges_0%2012%203%2020.doc) Completed with the Practice Facilitator – details to be submitted to [RIDOH@ctc-ri.org](mailto:RIDOH@ctc-ri.org) |
| Report de-identified practice screening rates and proportion of positive screens quarterly and by zip code | **Provisional Deadlines: July 9, 2021**  **October 8, 2021**  **January 14, 2022**  **April 8, 2022** | Submit via link at: [MomsPRN Data Reporting](https://www.tfaforms.com/4772053)  Alternative: Submit using [Excel Spreadsheet](https://www.ctc-ri.org/sites/default/files/uploads/12.%20RI%20MomsPRN%20Measure%20Reporting%20Template%2003.15.21%20Version.xlsx) and email to: jarruda@ctc-ri.org |
| Test workflows and submit final workflows for implementing screenings for depression, anxiety and substance use using validated screening tools | July 30, 2021 |  |
| In conjunction with the QI practice facilitator, submitted completed P-D-S-A identifying results of improvement activities to optimize perinatal behavioral health screening treatment and referral | Due by August 31, 2021 | [Plan-Do-Study-Act (PDSA)](https://www.ctc-ri.org/sites/default/files/uploads/4.%20PDSAWorksheetforTestingChanges_0%2012%203%2020.doc) Completed with the Practice Facilitator – details to be submitted to [RIDOH@ctc-ri.org](mailto:RIDOH@ctc-ri.org) |
| Practice QI team attendance and participation at Sept (mid) learning session | Sept 2021 TBD  7:30 – 9AM |  |
| In conjunction with the QI practice facilitator, report on outcomes quality improvement activities to optimize perinatal behavioral health screening, treatment and referral | Due by: March 15, 2022 | [Plan-Do-Study-Act (PDSA](https://www.ctc-ri.org/sites/default/files/uploads/4.%20PDSAWorksheetforTestingChanges_0%2012%203%2020.doc)) Completed with the Practice Facilitator – details to be submitted to [RIDOH@ctc-ri.org](mailto:RIDOH@ctc-ri.org) |
| Practice QI team attendance and participation with additional in-person learning network meetings and other trainings as needed/requested | TBD |  |
| Providers complete post efficacy survey and HRSA survey  Practice team completes post efficacy survey with practice facilitator | RIDOH Surveys by April 1, 2022  HRSA survey by Dec 2021-Jan 2022 |  |
| Practice QI team attendance and participation at closing learning session | April TBD 2022  7:30 – 9AM |  |