| New Pediatric Practice Transfer of Care Quality Improvement Milestone Summary |  |  |  |
| --- | --- | --- | --- |
| The timeframe to accomplish the transfer is brief. In months, 5-7, the last pediatric visit with each patient will be completed. An optional joint communication/telehealth call between sending and receiving PCPs with transferring patient will happen before the initial adult visit, which will start in months 8-11. If joint communication/telehealth call is not completed, practice will plan for other youth/young adult engagement activity. |  |  |  |
| Component | Deliverable | Timeframe Due Dates | Notes |
| Form Health Care Transition Quality Improvement Team and Confirm Connection with Adult Practice | - Identify members of the practice quality improvement (QI) team. The team should consist of 3 to 4 staff in different roles such as practice clinical champion, nurse care manager/care coordinator, practice manager, and/or IT representative if available. - Establish connection with adult primary care practice who will be accepting 7 transferring patients, with at least 3 patients with special health care needs. | Completed as part of submitted application |  |
| Project Start-Up | - Pediatric practice completes Got Transition’s Current Assessment of HCT Activities | November 7, 2023 | Due November 7, 2023 Current Pediatric Assessment of HCT Activities |
| Project Start-Up | - Team champion/team member(s)Participate in kick-off meeting with pediatric and adult awardees to review project plan. - Schedule regular monthly team meetings with Practice Facilitator (PF) | November 14, 2023 | Kickoff meeting Zoom |
| Identify and Invite Potential Eligible Patients Ready to Transfer | - Identify 7 young adults interested in transferring to adult practice. (3 patients with special health needs) - Invite these 7 patients to participate, explaining time frame and added transition assistance to be provided, e.g.: - medical summary - communication between pediatric/adult doctors, - facilitated integration into adult care (See sample medical summary form) - integration of youth/family goal - Create a simple tracking sheet (registry) to monitor date of last pediatric visit, joint communication/telehealth call, and initial adult visit and receipt of core elements 4,5, and 6. - Share progress in monthly QI meeting. (see sample registry form) | Months 1-2 Nov. 2023 Dec 2023 | Transitioning Youth to an Adult Health Care Clinician-Implementation Guide (gottransition.org) See: Transitioning Youth to an Adult Health Care Clinician Core Element 4 - Transition Planning (update plan of care with youth’s goal) |
| Develop Transfer of Care Improvement Plan for Transferring Patients | - Review Got Transition’s 6 Core Elements, with special attention to Core Elements 4,5,6 - Utilize suggested tools that can be customized by the practice. - Use Plan-Do-Study-Act (PDSA) cycles for Core Elements 4, 5, and 6, summarized in detail below. - Explore billing and coding for transition services. - Share progress in monthly QI meeting. | Months 1-4 Nov. 2023 Dec 2023 Jan 2024 Feb 2024 | Core Element 4- Transition Planning Core Element 5- Transfer of Care Core Element 6 – Transfer Completion 2023 Coding and Payment Tip Sheet for Transition from Pediatric to Adult Health Care |
| Develop Content and Process for Transition Planning (Core Element 4), with PDSA Cycle | - Customize content and process for Transition Planning (Core Element 4), including: - preparation of medical summary to be shared with patient and adult PCP inclusive of what matters to the youth/family (goals/plan of care) - discussion with patient about plans for timing of transfer to adult care - changes in privacy at age 18. (See sample check list) - Complete a PDSA on customized content and process for Core Element #4. - Share approach at monthly QI meeting. | Month 2 Dec 2023 | Six Core Elements Implementation Guide for Transition Planning Turning 18: What It Means for Your Health |
| Develop Content and Process for Transfer of Care (Core Element 5), including goals for care for the youth and/or families with PDSA Cycle | - Customize content and process for Transfer of Care (Core Element 5), deciding on what should be included in the transfer package. Work with adult PCP about content for joint communication/ telehealth call transferring patient. - Decide on residual role of pediatric PCP before initial adult visit (eg, refills, taking care of acute needs). - Complete a PDSA on customized content and process for Core Element #5. - Share approach at monthly QI meeting. | Month 3 Jan 2024 | Six Core Elements Implementation Guide for Transfer of Care Transition Readiness Assessment (not required, for reference only) Sample Joint Telehealth Visit Script |
| Develop Content and Process for Transfer Completion (Core Element 6), with PDSA Cycle | - Customize content and process for Transfer Completion (Core Element 6), including plan for confirming completion of initial adult visit, offering time-limited consultation to adult PCP (if needed). - Complete a PDSA on customized content and process for Core Element #6. - Share approach at monthly QI meeting. | Month 4 Feb 2024 | Six Core Elements Implementation Guide for Transfer Completion Submit PDSA (including goals for care for the youth) to deliverables@ctc-ri.org by March 12, 2024. |
| Learning collaborative Joint meetings* | Team champion/designee/team members actively participate in Learning Collaborative Joint Meetings (3 total) | March 26, 2024 | Learning Collaborative meeting Zoom Provider champion or team member to present on experience with program to date, PDSA and status of transitions |
| Start transfer process with 7 Pediatric Patients, 3 must have special health care needs | - Schedule and complete final pediatric visits. - Following final pediatric visits, complete transfer package and share with patient and adult PCP. - Coordinate with adult practice and patient to schedule a joint communication/telehealth call following last pediatric visit and before initial adult visit. - Share progress in monthly QI meeting. | Months 5-8 March 2024 April 2024 May 2024 June 2024 | Sample Telehealth Toolkit Link to be provided Submit PPT to deliverables@ctc-ri.org by June 11, 2024 |
| Learning collaborative Joint meetings* | Team champion/designee/team members actively participate in Learning Collaborative Joint Meetings (3 total) | June 25, 2024 | Learning Collaborative meeting Zoom Provider champion or team member to present on experience with program to date, PDSA and status of transitions |
| (Adult PCPs) Start Integration into Adult Care | - Schedule and complete initial adult visits – discuss who is responsible for scheduling visit (patient, adult practice, pediatric practice?) - Pediatric practice communicates with adult practice to confirm initial appointment made. - Intentionally reviews and discusses youth goal/plan of care - Adult practice administers anonymous HCT Feedback Survey to young adults at initial visit. - Pediatric practice communicates with adult practice to confirm completion of HCT Feedback Survey by young adult, following the initial adult visit. - Share progress in monthly QI meeting. | Months 9-12 July 2024 August 2024 September 2024 October 2024 | Young Adult HCT Feedback Survey as patients are seen. Submit final PDSA with PPT to deliverables@ctc-ri.org by October 9, 2024 Submit current Pediatric Assessment of HCT Activities by October 9, 2024 |
| Learning collaborative Joint meetings* | Learning Collaborative Joint Meetings (final) - Complete Current Assessment of HCT Activities - Review lessons learned and plans for sustainability and spread. - Share progress in monthly QI meeting. | October 22, 2024 | Learning Collaborative meeting Zoom Provider champion or team member to present on experience with program to date, PDSA and status of transitions |
| Learning Collaborative Project Evaluation | - Complete Project and Practice Facilitation Evaluation | November 2024 | https://www.surveymonkey.com/r/TOC2023Cohort3 |
| Learning Collaborative Dates | - Kickoff – Introductions - March – PDSA (Aim & Plan) - June – PDSA update (Do, Study, Act) - October – Lessons Learned, Plans for Sustainability and Spread, Youth Feedback | November 14, 2023 7:30-9:00AM March 26, 2024 June 25, 2024 October 22, 2024 7:30-8:30AM | Zoom |

*Additional Joint Learning Collaborative may be added based on the team learning needs