# ATTACHMENT A: CTC Pediatric Weight Management Milestones Summary

# September 2022-August 2023

|  |  |  |
| --- | --- | --- |
|  | **Important Dates** | **Notes** |
| ***Required Meetings*** |  |  |
| **Learning Collaborative Meetings:**   1. **Kickoff + ECHO #1** 2. **Wrap-up meetings/ECHO #11 & #12**   **ECHO Learning Sessions #2-#10**  **12 Monthly Meetings with Practice Facilitator** | Sept. 22, 2022 7:30-9am  July 20, 2023 & August 17, 2023 7:30-8:30am  3rd Thursday/Month 7:30-8:30  From October, 2022 – June, 2023  To be scheduled by practices individually  Sept 2022 – August 2023 | The expectation is that all of these will be virtual meetings; Zoom invitations will be sent out by CTC. |
| ***Case Presentations*** |  |  |
| **Each practice to present at least 1 patient case at monthly ECHO Learning Session.** | Date to be assigned | [Case Form Template](https://www.ctc-ri.org/sites/default/files/uploads/case%20form%20powerpoint.pptx)  Submit 2 weeks prior to ECHO Learning Session to: deliverables@ctc-ri.org |
| **Each practice to present 1 patient success story at wrap-up meetings** | Date to be assigned  July 20, 2023 & August 17, 2023 7:30-8:30 | Template to be provided  Success story to be submitted July 6, 2023 or August 3, 2023 |
| ***Assessments*** |  |  |
| **Complete Learning Collaborative Pre-Assessment to be completed by all members of the team** | Submitted with Participative Agreement  Due August 31, 2022 | **Is there a submit to for this?** |
| **Complete Learning Collaborative Post-Assessment to be completed by all members of the team** | Due August 31, 2023 | **Submit to:** deliverables@ctc-ri.org |
| **Complete post-ECHO evaluations (by all team members who attended the ECHO)** | Monthly, immediately following each ECHO session |  |
| **(Optional) Complete final evaluation for CME/MOC part 4** | Due August 30, 2023 |  |
| ***PDSA*** |  |  |
| **Identify a PDSA Topic for improving 1 of the following Pediatric Weight Mgt best practices:**   1. **IBH Enhancement**: Establish monthly case consultations with IBH team 2. **Primary Prevention:** Establishstandardized protocol to address healthy habits for children 0-2 years old at WCV 3. **Assessment**: Improve assessment of factors that impact pediatric weight by incorporating a standardized assessment into WCV or follow up visit 4. **Patient Identification**: Develop a workflow for identifying and tracking patients with obesity/overweight, including those who are referred to, and seen by, IBHC 5. **Treatment/intervention**: set up a protocol for patients who are overweight/obese to be seen more than once/year by a provider | Due February 15, 2023 |  |
| **Midpoint PDSA Data report** | Due May 15, 2023 | **Submit to:** deliverables@ctc-ri.org |
| **Final PDSA reporting out on progress, challenges and results/outcomes** | Due August 15, 2023 | **Submit to:** deliverables@ctc-ri.org |
|  |  |  |