|  |
| --- |
| **PCMH Kids SBIRT Milestone Document** |
| **Deliverable** | **Date Due** | **Notes** |
| *Sign Cooperative Agreement and attend first meeting.* | Signed agreement: 3/15/18First meeting 3/28/18 |  |
| *SBIRT Adolescent Practice Assessment* <https://www.surveymonkey.com/r/HSLR8V2> | March 20, 2018 |  |
| *Complete* [*Kognito on-line learning modules*](https://kognitocampus.com/)*: To be done by the clinical staff that will be screening adolescents for substance use disorders made available through RIC SBIRT program* | June 11, 2018 |  |
| *Attend a 2-hour workshop on motivational interviewing;* | TBD |  |
| *Submit* [*work plan with AIM statement*](file:///%5C%5Cumwssnas01.umassmed.edu%5COPD-CSI%24%5C21%20IBH%20Pilot%20Projects%5CPediatrics%5C2018%20SBIRT%5CCommunications%20and%20Deliverables%5CSBIRT%20Learning%20Collaborative%20AIM%2C%20work%20plan%2C%20baseline%20measure.docx.doc) *and baseline data* | June 11, 2018(data from Mar, Apr, and May) | Submit to ctc-ri@ctc-ri.org |
| *Submit* [*second data point worksheet*](file:///%5C%5Cumwssnas01.umassmed.edu%5COPD-CSI%24%5C21%20IBH%20Pilot%20Projects%5CPediatrics%5C2018%20SBIRT%5CCommunications%20and%20Deliverables%5CSBIRT%20Learning%20Collaborative%20AIM%2C%20work%20plan%2C%20baseline%20measure%20%28second%20workplan%29.docx.doc) | September 10, 2018(data from Jun, Jul, and Aug) | Submit to ctc-ri@ctc-ri.org |
| *Submit* [*third data point worksheet*](file:///%5C%5Cumwssnas01.umassmed.edu%5COPD-CSI%24%5C21%20IBH%20Pilot%20Projects%5CPediatrics%5C2018%20SBIRT%5CCommunications%20and%20Deliverables%5CSBIRT%20Learning%20Collaborative%20AIM%2C%20work%20plan%2C%20baseline%20measure%20%28third%20workplan%29.docx.doc) | December 10, 2018(data from Sep, Oct, and Nov) | Submit to ctc-ri@ctc-ri.org |
| *Submit* [*final data point worksheet*](file:///%5C%5Cumwssnas01.umassmed.edu%5COPD-CSI%24%5C21%20IBH%20Pilot%20Projects%5CPediatrics%5C2018%20SBIRT%5CCommunications%20and%20Deliverables%5CSBIRT%20Learning%20Collaborative%20AIM%2C%20work%20plan%2C%20baseline%20measure%20%28fourth%20workplan%29.docx.doc) | March 11, 2019(data from Dec, Jan, and Feb) | Submit to ctc-ri@ctc-ri.org |
| *Attend quarterly CTC Pediatric Behavioral Health meeting and report AIM statement measure results quarterly at CTC Behavioral Health meetings*  | June 14, 2018,September 13, 2018, December 13, 2018,March 14, 2019 | *June 14, 2018*-practices will share baseline measure and share activities of work plan; *September 13, 2018*-practices will share second data point and report on progress in work plan; *December 13, 2018*- practices will share third data point and report on progress in work plan; and*March 14, 2019* - final meeting where practices should present fourth data point and a summary of the year’s activities in this learning collaborative. |
| *Provide opportunity for medical residents/medical students to participate in practice learning as requested* |  |  |
| *Meet with QI Practice Facilitator and Clinical Coaches who will be assigned to work with your practice 3 hours per quarter****.*** | March-JuneJuly-SeptOct-DecJan-March | QI Practice facilitator to assist team with work plan with AIM statement.Clinical Coach to assist with team concerns in screening adolescents for SUD and facilitating treatment plans. |